## Sheet1
PROJECT TITLE :BUY AND SELL
Date of Authorization: 1st Jan 2025
Project Start Date: 1st Jan 2025					Projected Finish Date: 2nd April 2025

Key Schedule Milestone:
	·Complete user Interface before 1st March
	·Complete Database Connectivity before 15th April
	·Complete Prototype before 1st may

Project Justification:
The rise in online shopping has created a significant opportunity for businesses to tap into a global market. An e-commerce website allows businesses to extend their reach beyond physical locations, increase sales, and provide customers with the convenience of shopping anytime, anywhere. This project will meet the growing demand for digital shopping experiences by offering a user-friendly, secure, and scalable online platform for products and services.

Objectives:
	Design an intuitive home page.
	To enable online payments and shopping cart functionality to allow customers to easily purchase products or services.
	To design and develop a fully functional e-commerce website that is user-friendly and secure.
	Integrate a communication feature for announcements and notices.
	Ensure mobile responsiveness and user-friendly navigation.

High Level Requirement:
	1)The website must include a homepage,item section,history,etc.
	2)It should be designed to be mobile-friendly.
	3)The website must be secure and follow best practices for data privacy.
	4)Include features like CAP theorem.
	5)The system should be easy to update by the administrator.

Roles and Responsibilities:
Name		Role		Position			Contact info
Dishant Pawar		Team Member		Senior Programmer			8830576315
MUKESH AMBANI		Sponsor		Executive			8830576316
Pruthviraj Bachhav		Team Member		Junior Programmer			8830576317
Bhavesh Patil		Manager		Head			8830576318

Sign-Off(Signature of above stake holders):
kamlesh		Dishant
Rakesh		Bhavesh