## Sheet1
PROJECT TITLE :ALL IN ONE CLASS WEBSITE
Date of Authorization: 5th Jan 2025
Project Start Date: 5th Jan 2025 |  |  |  | Projected Finish Date: 15th May 2025
Key Schedule Milestone:
·Complete user Interface before 5th March
·Complete Database Connectivity before 20th April
·Complete Prototype before 5th may
Project Justification:
The purpose of this project is to design and develop a class website that will provide easy access to the syllabus, student and teacher login portals, and other relevant class materials. This website will improve communication between students and teachers and enhance the overall learning experience. The justification for this project is to streamline course management, increase student engagement, and provide a central hub for class resources.
Objectives:
Design an intuitive home page.
Develop a syllabus page that is regularly updated.
Create secure student and teacher login portals for personalized access.
Integrate a communication feature for announcements and notices.
Ensure mobile responsiveness and user-friendly navigation.
High Level Requirement:
1)The website must include a homepage, syllabus, and secure login portals for students and teachers.
2)It should be designed to be mobile-friendly.
3)The website must be secure and follow best practices for data privacy.
4)Include features for announcements, assignment uploads, and grade tracking.
5)The system should be easy to update by the class administrator (teacher).
Roles and Responsibilities:
Name |  | Role | Position |  | Contact info
Dishant |  | Team Member | Senior Programmer |  | 123123123
Rakesh |  | Sponsor | Executive |  | 321321321
Prasad |  | Team Member | Junior Programmer |  | 234234234
Jayash |  | Manager | Head |  | 567567567
Sign-Off(Signature of above stake holders):
Dishant |  | Prasad
Rakesh |  | Jayash